## Sheet1
Screen | Task | Estimated Time | comment | Total
Auth (login in - logout - forget) | Design login screen - forget passward - signup | 6 | This also include init the project - init lang , firebase , common components | 77
| Implement authentication logic | 5
| Integrate with API | 3 | This include init the API integration among project
Navigation | Create reusable components (header - nav - drawer..etc) | 4
| Set up base navigation | 4
Cars | Design car list UI | 6
| Implement car data fetching | 4
| Integrate React native maps with car data fetching | 6
Charging solution | Design station map layout | 5
| Implement station fetching (API of the station location to integrate with maps) | 4
Home | Create home screen layout | 5
| Add requierd home navigation - also add user data | 5
Invoice | Design invoice | 5
| Implement invoice generation based on API | 4
Payment | Integrate payment API | 0 | bassed on profider
Loading | Create loading animation | 2 | will be nice to have
Settings | Design settings screen | 4
| Implement update user data | 5
WebsiteOptions
option 1 | https://themeforest.net/item/starty-nextjs-multipurpose-landing-template/54414255 |  | This what we choose
option 2 | https://preview.themeforest.net/item/bantec-it-service-technology-nextjs-template/full_screen_preview/53564689
option 3 | https://preview.themeforest.net/item/superio-job-board-react-nextjs-template/full_screen_preview/42719363
option 4 | https://preview.themeforest.net/item/prohealth-medical-and-healthcare-nextjs-template/full_screen_preview/50745875